## Slide 1
Project Planning
PRESSURE SENSOR PATCH
sdmay25-12
Advisor: Santosh Pandey
Client: BAE Systems
Lightning Talk 4:

## Slide 2
Project Overview
Objective
Develop a pressure sensor patch for adaptive sports athletes to monitor pressure levels and prevent pressure sores.
Target Users
Athletes with traumatic injuries at risk of pressure sores
Core Functionality
Real-time data collection, processing, and alert system via an app.
Key Features
Wireless connectivity to mobile devices, customizable pressure thresholds, and continuous monitoring, even when the app is closed.

## Slide 3
Project Management Style
Why Agile?
  Allows for continuous feedback and iterations from user testing.
  Flexibility in adapting to hardware and software changes, especially with sensor integration.
  Regular sprints to ensure progress and timely adjustments.

## Slide 4
Category | Details
Hardware Integration | Connect and test pressure sensors. Ensure that the sensors produce readable and logic data.
Mobile App Development | Design, implement, and test the mobile app (Android).
Wireless Connectivity | Integrate Bluetooth module (HC-05) to ensure data transfer between patch and app.
Data Processing | Develop algorithms to process pressure data and trigger alerts.
Testing & Validation | Simulate real-world conditions and conduct user testing with adaptive athletes.
Task Decomposition

## Slide 5
Week | Week 2 | Week 4 | Week 5 | Week 6 (Current) | Upcoming (Week 8)
Accomplished | Researched relevant pressure sensors on the market and ordered multiple sensors for testing. | Initial app UI/UX design and user flow created. | Tested sensors for accuracy and responsiveness | Developed the basic foundation for the mobile application, integrating core UI elements and preparing for sensor data integration. | Complete Bluetooth connectivity integration and start real-time data transmission between patch and app.
Key Milestones

## Slide 6
  Accuracy of Pressure Readings: Measured through controlled tests.
  User Experience: Athlete feedback on ease of use and responsiveness.
  Alert Timeliness: Ensure alerts are triggered within seconds of detecting harmful pressure levels.
  Battery Life: Optimize system for extended use without frequent charging.
  Application: User friendly & easy to navigate
Metrics & Evaluation Criteria

## Slide 7
Risk
Sensor malfunctions or inaccuracies
Bluetooth connectivity issues in dynamic sports environments
App crashes during monitoring
Mitigation
Thorough sensor testing before deployment; redundant sensors as backups.
Testing in various environments and improving signal range.
Regular stress testing and memory management in the app code.
Key Risks & Mitigation

## Slide 8
Conclusion
Summary
Agile development process supports iterative improvements, real-world testing, and adaptability.
Next Steps
Connect the sensors to the application. Get logical readings and analyze data
Goal
Deliver a reliable solution for athletes by April 2025. Deliver a prototype by the end of Fall 2024 semester.